## Start Here
Step 1 · Excel practice workbook
Scenario: you're the new data analyst at a council. Three teams keep separate spreadsheets about the same projects, and none of them agree. Your job: clean, match and check them.
DATA SHEETS (don't edit)
Register_A | The PMO project register: 25 rows, project IDs PRJ-001 to PRJ-024. Contains a duplicate, a missing owner, messy text and a date error.
Register_B | The finance register: different codes (FIN-…), messy titles, and some projects missing or extra.
Risk_Log | 40 risks linked to projects. Some have no owner, some are overdue, two point to projects that don't exist.
PRACTICE SHEETS
Ex1_Clean | Lessons 2–3: clean text and flag problems with TRIM, PROPER, IF, COUNTIF.
Ex2_Crosswalk | Lessons 4–5: match Register_A to Register_B with INDEX/MATCH or XLOOKUP, then compare budgets.
Ex3_Risks | Lessons 3, 4, 8: risk scores, ratings, overdue flags, orphan checks.
Ex4_Summary | Lesson 4: summary counts and totals with COUNTIFS and SUMIFS.
Answers | Worked formulas for every exercise. Only look after you've tried!
LEGEND
Yellow cells | Your answer cells: type your formula in these.
Green row | A worked example showing the pattern. Copy it down, then work out the rest yourself.
PIVOT TABLE TASKS (Lesson 6)
Pivot 1 | Click inside Register_A → Insert → PivotTable. Rows = Division, Values = Sum of Budget. Which division spends most?
Pivot 2 | Same pivot: add Status to Columns. How many Red projects does each division have? (Change Values to Count.)
Pivot 3 | From Risk_Log: Rows = Owner, Columns = Status, Values = Count of Risk ID. Who owns the most open risks?
MINI PROJECT (Lesson 10)
Deliverables | 1) Finished crosswalk 2) Issue log listing every problem you found (sheet, row, problem, suggested fix) 3) A 5-line summary for your manager.

## Register_A
Project ID | Initiative Name | Owner | Division | Start Date | End Date | Budget ($) | Status
PRJ-001 | Customer Portal Upgrade | Priya Sharma | Digital | 2025-06-05 | 2026-04-23 | 455000 | Green
PRJ-002 | Payroll System Replacement | Liam O'Brien | Digital | 2025-06-19 | 2025-11-15 | 360000 | Green
PRJ-003 | Records Digitisation | James Wilson | Community | 2025-07-14 | 2025-12-16 | 190000 | Green
PRJ-004 | Cyber Security Uplift | Priya Sharma | Community | 2025-10-04 | 2026-05-26 | 440000 | amber
PRJ-005 | Fleet Telematics Rollout | Mei Chen | Operations | 2025-04-02 | 2026-05-12 | 585000 | Complete
PRJ-006 | Data Warehouse Migration | Aisha Khan | Corporate | 2025-03-18 | 2025-09-14 | 405000 | Green
PRJ-007 | Mobile Inspections App |  | Digital | 2025-10-19 | 2027-01-09 | 160000 | Green
PRJ-008 | Office Network Refresh | Daniel Park | Community | 2025-10-02 | 2026-12-12 | 170000 | Red
PRJ-009 | Grants Management System | Aisha Khan | Corporate | 2025-08-19 | 2026-08-06 | 270000 | Amber
PRJ-009 | Grants Management System | Aisha Khan | Corporate | 2025-08-19 | 2026-08-06 | 270000 | Amber
PRJ-010 | Asset Register Cleanup | Aisha Khan | Community | 2025-12-25 | 2026-08-26 | 90000 | Red
PRJ-011 | Workforce Planning Tool | James Wilson | Digital | 2025-12-15 | 2026-09-08 | 425000 | Complete
PRJ-012 | Call Centre Modernisation | Daniel Park | Community | 2025-03-25 | 2025-02-23 | 135000 | Green
PRJ-013 | Identity & Access Management | Tom Nguyen | Operations | 2025-11-03 | 2027-03-29 | 395000 | Red
PRJ-014 | Budget Reporting Automation | Daniel Park | Digital | 2025-10-16 | 2026-12-06 | 550000 | Green
PRJ-015 | website accessibility fixes | James Wilson | Digital | 2025-05-16 | 2026-09-04 | 465000 | Red
PRJ-016 | Cloud Email Migration | Daniel Park | Operations | 2025-11-19 | 2027-03-02 | 565000 | Complete
PRJ-017 | Contract Management Platform | Tom Nguyen | Corporate | 2025-11-12 | 2026-03-23 | 335000 | Green
PRJ-018 | Service Desk Replacement | Aisha Khan | Corporate | 2025-08-02 | 2026-03-21 | 530000 | Amber
PRJ-019 | GIS Mapping Upgrade | Mei Chen | Community | 2025-07-13 | 2026-07-22 | 90000 | Complete
PRJ-020 | Procurement Portal | Sarah Jones | Operations | 2025-09-09 | 2026-03-18 | 560000 | Complete
PRJ-021 | Document Management Upgrade | Mei Chen | Digital | 2025-06-22 | 2026-05-02 | 185000 | Amber
PRJ-022 | Data Governance Framework | Priya Sharma | Community | 2025-03-08 | 2026-06-08 | 185000 | Amber
PRJ-023 | Electric Vehicle Charging | Sarah Jones | Operations | 2025-05-10 | 2025-09-09 | 130000 | Red
PRJ-024 | Council Meeting Livestream | Priya Sharma | Community | 2025-03-23 | 2026-04-10 | 435000 | Complete
Click inside Register_A → Insert → PivotTable. Rows = Division, Values = Sum of Budget. Which division spends most?

## Pivot_Status
Sum of Budget ($) | Column Labels
Row Labels | Amber | amber | Complete | Green | Red | Grand Total
Community | 185000 | 440000 | 525000 | 325000 | 260000 | 1735000
Corporate | 1070000 |  |  | 740000 |  | 1810000
Digital | 185000 |  | 425000 | 1525000 | 465000 | 2600000
Operations |  |  | 1710000 |  | 525000 | 2235000
Grand Total | 1440000 | 440000 | 2660000 | 2590000 | 1250000 | 8380000

## Register_B
Finance Code | Project Title | Approved Budget ($) | Forecast ($) | Actual to Date ($) | Match Key (you fill) =LOWER(TRIM(B2))
FIN-103 | RECORDS DIGITISATION | 190000 | 169000 | 105000 | records digitisation
FIN-115 | contract management platform | 335000 | 399000 | 321000 | contract management platform
FIN-114 | cloud email migration | 535000 | 626000 | 457000 | cloud email migration
FIN-113 | Website Accessibility Fixes | 465000 | 429000 | 372000 | website accessibility fixes
FIN-107 | MOBILE INSPECTIONS APP | 160000 | 172000 | 149000 | mobile inspections app
FIN-102 | Payroll System Replacement | 345000 | 301000 | 104000 | payroll system replacement
FIN-118 | DOCUMENT MANAGEMENT UPGRADE | 185000 | 197000 | 148000 | document management upgrade
FIN-122 | Parking Sensor Trial | 60000 | 52000 | 30000 | parking sensor trial
FIN-111 | IAM Program | 395000 | 439000 | 315000 | iam program
FIN-108 | Grants Management System | 270000 | 264000 | 76000 | grants management system
FIN-106 | Data Warehouse Migration | 405000 | 468000 | 295000 | data warehouse migration
FIN-110 | Call Centre Modernisation | 135000 | 129000 | 39000 | call centre modernisation
FIN-120 | Council Livestreaming | 435000 | 482000 | 173000 | council livestreaming
FIN-104 | Cyber Security Uplift | 440000 | 374000 | 114000 | cyber security uplift
FIN-105 | Fleet Telematics Rollout | 585000 | 692000 | 436000 | fleet telematics rollout
FIN-121 | Library Self-Checkout Kiosks | 95000 | 98000 | 41000 | library self-checkout kiosks
FIN-109 | Asset Register Cleanup | 90000 | 108000 | 57000 | asset register cleanup
FIN-119 | DATA GOVERNANCE FRAMEWORK | 185000 | 209000 | 162000 | data governance framework
FIN-101 | Customer Portal Upgrade | 455000 | 450000 | 123000 | customer portal upgrade
FIN-112 | Budget Reporting Automation | 550000 | 627000 | 196000 | budget reporting automation
FIN-116 | service desk replacement | 530000 | 547000 | 457000 | service desk replacement
FIN-117 | procurement portal | 530000 | 551000 | 304000 | procurement portal

## Pivot_risk
Count of Risk ID | Column Labels
Row Labels | Closed | Monitoring | Open | Grand Total
Aisha Khan |  |  | 5 | 5
Daniel Park | 1 | 1 | 1 | 3
James Wilson |  |  | 4 | 4
Liam O'Brien |  | 3 | 2 | 5
Mei Chen |  |  | 1 | 1
Priya Sharma | 2 |  | 4 | 6
Sarah Jones | 1 | 1 | 2 | 4
Tom Nguyen |  | 2 | 1 | 3
(blank) | 2 | 1 | 6 | 9
Grand Total | 6 | 8 | 26 | 40

## Risk_Log
Risk ID | Project ID | Description | Owner | Likelihood (1-5) | Impact (1-5) | Next Review | Status
R-001 | PRJ-010 | Scope creep | Daniel Park | 5 | 5 | 2026-12-01 | Monitoring
R-002 | PRJ-020 | Data migration errors | James Wilson | 1 | 4 | 2026-12-23 | Open
R-003 | PRJ-015 | Budget overrun | Sarah Jones | 3 | 1 | 2026-12-24 | Monitoring
R-004 | PRJ-014 | Security vulnerability found | James Wilson | 2 | 2 | 2026-07-01 | Open
R-005 | PRJ-018 | Stakeholder resistance | Mei Chen | 5 | 5 | 2026-09-22 | Open
R-006 | PRJ-031 | Licensing cost increase |  | 2 | 1 | 2026-06-26 | Open
R-007 | PRJ-016 | Budget overrun | Sarah Jones | 2 | 2 | 2026-06-09 | Open
R-008 | PRJ-009 | Licensing cost increase | Liam O'Brien | 5 | 3 | 2026-08-18 | Monitoring
R-009 | PRJ-005 | Vendor delivery delay | Tom Nguyen | 4 | 5 | 2026-12-17 | Monitoring
R-010 | PRJ-016 | Budget overrun |  | 2 | 5 | 2026-10-01 | Monitoring
R-011 | PRJ-024 | Budget overrun | Priya Sharma | 2 | 2 | 2026-07-16 | Closed
R-012 | PRJ-023 | Key staff unavailable |  | 1 | 3 | 2026-11-17 | Closed
R-013 | PRJ-017 | Stakeholder resistance | James Wilson | 5 | 1 | 2026-07-07 | Open
R-014 | PRJ-002 | Key staff unavailable |  | 4 | 5 | 2026-06-25 | Open
R-015 | PRJ-014 | Data migration errors |  | 5 | 5 | 2026-07-23 | Open
R-016 | PRJ-014 | Licensing cost increase |  | 4 | 5 | 2026-07-23 | Closed
R-017 | PRJ-009 | Licensing cost increase | Liam O'Brien | 4 | 2 | 2026-09-04 | Monitoring
R-018 | PRJ-014 | Data migration errors | James Wilson | 2 | 4 | 2026-06-07 | Open
R-019 | PRJ-004 | Budget overrun | Tom Nguyen | 2 | 3 | 2026-07-15 | Open
R-020 | PRJ-023 | Key staff unavailable | Sarah Jones | 4 | 2 | 2026-11-27 | Open
R-021 | PRJ-006 | Security vulnerability found |  | 4 | 3 | 2026-09-07 | Open
R-022 | PRJ-010 | Key staff unavailable | Tom Nguyen | 1 | 3 | 2026-10-15 | Monitoring
R-023 | PRJ-045 | Vendor delivery delay | Sarah Jones | 3 | 5 | 2026-10-10 | Closed
R-024 | PRJ-003 | Key staff unavailable | Liam O'Brien | 1 | 1 | 2026-08-09 | Open
R-025 | PRJ-024 | Budget overrun | Aisha Khan | 2 | 4 | 2026-12-22 | Open
R-026 | PRJ-012 | Budget overrun |  | 5 | 5 | 2026-09-23 | Open
R-027 | PRJ-003 | Integration failure | Priya Sharma | 2 | 4 | 2026-06-09 | Open
R-028 | PRJ-020 | Key staff unavailable | Aisha Khan | 1 | 5 | 2026-12-08 | Open
R-029 | PRJ-009 | Key staff unavailable | Daniel Park | 1 | 3 | 2026-10-14 | Open
R-030 | PRJ-019 | Budget overrun | Priya Sharma | 5 | 2 | 2026-06-06 | Open
R-031 | PRJ-002 | Budget overrun | Liam O'Brien | 3 | 3 | 2026-10-25 | Open
R-032 | PRJ-009 | Stakeholder resistance |  | 2 | 3 | 2026-08-26 | Open
R-033 | PRJ-009 | Vendor delivery delay | Priya Sharma | 1 | 5 | 2026-10-07 | Closed
R-034 | PRJ-015 | Scope creep | Daniel Park | 1 | 4 | 2026-11-16 | Closed
R-035 | PRJ-012 | Licensing cost increase | Aisha Khan | 2 | 2 | 2026-08-07 | Open
R-036 | PRJ-012 | Data migration errors | Priya Sharma | 2 | 1 | 2026-06-21 | Open
R-037 | PRJ-013 | Budget overrun | Priya Sharma | 1 | 4 | 2026-12-17 | Open
R-038 | PRJ-019 | Scope creep | Aisha Khan | 1 | 4 | 2026-07-06 | Open
R-039 | PRJ-014 | Vendor delivery delay | Aisha Khan | 3 | 3 | 2026-10-11 | Open
R-040 | PRJ-002 | Integration failure | Liam O'Brien | 3 | 2 | 2026-06-11 | Monitoring

## Ex1_Clean
Project ID | Initiative Name (raw) | Owner (raw) | Status (raw) | Clean Name =TRIM(PROPER()) | Clean Status | Owner Missing? | Duplicate ID? | Dates OK?
PRJ-001 | Customer Portal Upgrade | Priya Sharma | Green | Customer Portal Upgrade | Green | OK | OK | OK
PRJ-002 | Payroll System Replacement | Liam O'Brien | Green | Payroll System Replacement | Green | OK | OK | OK
PRJ-003 | Records Digitisation | James Wilson | Green | Records Digitisation | Green | OK | OK | OK
PRJ-004 | Cyber Security Uplift | Priya Sharma | amber | Cyber Security Uplift | Amber | OK | OK | OK
PRJ-005 | Fleet Telematics Rollout | Mei Chen | Complete | Fleet Telematics Rollout | Complete | OK | OK | OK
PRJ-006 | Data Warehouse Migration | Aisha Khan | Green | Data Warehouse Migration | Green | OK | OK | OK
PRJ-007 | Mobile Inspections App | 0 | Green | Mobile Inspections App | Green | OK | OK | OK
PRJ-008 | Office Network Refresh | Daniel Park | Red | Office Network Refresh | Red | OK | OK | OK
PRJ-009 | Grants Management System | Aisha Khan | Amber | Grants Management System | Amber | OK | DUPLICATE | OK
PRJ-009 | Grants Management System | Aisha Khan | Amber | Grants Management System | Amber | OK | DUPLICATE | OK
PRJ-010 | Asset Register Cleanup | Aisha Khan | Red | Asset Register Cleanup | Red | OK | OK | OK
PRJ-011 | Workforce Planning Tool | James Wilson | Complete | Workforce Planning Tool | Complete | OK | OK | OK
PRJ-012 | Call Centre Modernisation | Daniel Park | Green | Call Centre Modernisation | Green | OK | OK | END BEFORE START
PRJ-013 | Identity & Access Management | Tom Nguyen | Red | Identity & Access Management | Red | OK | OK | OK
PRJ-014 | Budget Reporting Automation | Daniel Park | Green | Budget Reporting Automation | Green | OK | OK | OK
PRJ-015 | website accessibility fixes | James Wilson | Red | Website Accessibility Fixes | Red | OK | OK | OK
PRJ-016 | Cloud Email Migration | Daniel Park | Complete | Cloud Email Migration | Complete | OK | OK | OK
PRJ-017 | Contract Management Platform | Tom Nguyen | Green | Contract Management Platform | Green | OK | OK | OK
PRJ-018 | Service Desk Replacement | Aisha Khan | Amber | Service Desk Replacement | Amber | OK | OK | OK
PRJ-019 | GIS Mapping Upgrade | Mei Chen | Complete | GIS Mapping Upgrade | Complete | OK | OK | OK
PRJ-020 | Procurement Portal | Sarah Jones | Complete | Procurement Portal | Complete | OK | OK | OK
PRJ-021 | Document Management Upgrade | Mei Chen | Amber | Document Management Upgrade | Amber | OK | OK | OK
PRJ-022 | Data Governance Framework | Priya Sharma | Amber | Data Governance Framework | Amber | OK | OK | OK
PRJ-023 | Electric Vehicle Charging | Sarah Jones | Red | Electric Vehicle Charging | Red | OK | OK | OK
PRJ-024 | Council Meeting Livestream | Priya Sharma | Complete | Council Meeting Livestream | Complete | OK | OK | OK

## Ex2_Crosswalk
Project ID | Initiative Name | Budget A ($) | Match Key (clean name) | Finance Code | Budget B ($) | Difference ($) | Result
PRJ-001 | Customer Portal Upgrade | 455000 | customer portal upgrade | FIN-101 | 455000 | 0 | Match
PRJ-002 | Payroll System Replacement | 360000 | payroll system replacement | FIN-102 | 345000 | -15000 | Budget mismatch
PRJ-003 | Records Digitisation | 190000 | records digitisation | FIN-103 | 190000 | 0 | Match
PRJ-004 | Cyber Security Uplift | 440000 | cyber security uplift | FIN-104 | 440000 | 0 | Match
PRJ-005 | Fleet Telematics Rollout | 585000 | fleet telematics rollout | FIN-105 | 585000 | 0 | Match
PRJ-006 | Data Warehouse Migration | 405000 | data warehouse migration | FIN-106 | 405000 | 0 | Match
PRJ-007 | Mobile Inspections App | 160000 | mobile inspections app | FIN-107 | 160000 | 0 | Match
PRJ-008 | Office Network Refresh | 170000 | office network refresh | NOT FOUND |  |  | Missing in finance
PRJ-009 | Grants Management System | 270000 | grants management system | FIN-108 | 270000 | 0 | Match
PRJ-009 | Grants Management System | 270000 | grants management system | FIN-108 | 270000 | 0 | Match
PRJ-010 | Asset Register Cleanup | 90000 | asset register cleanup | FIN-109 | 90000 | 0 | Match
PRJ-011 | Workforce Planning Tool | 425000 | workforce planning tool | NOT FOUND |  |  | Missing in finance
PRJ-012 | Call Centre Modernisation | 135000 | call centre modernisation | FIN-110 | 135000 | 0 | Match
PRJ-013 | Identity & Access Management | 395000 | identity & access management | NOT FOUND |  |  | Missing in finance
PRJ-014 | Budget Reporting Automation | 550000 | budget reporting automation | FIN-112 | 550000 | 0 | Match
PRJ-015 | website accessibility fixes | 465000 | website accessibility fixes | FIN-113 | 465000 | 0 | Match
PRJ-016 | Cloud Email Migration | 565000 | cloud email migration | FIN-114 | 535000 | -30000 | Budget mismatch
PRJ-017 | Contract Management Platform | 335000 | contract management platform | FIN-115 | 335000 | 0 | Match
PRJ-018 | Service Desk Replacement | 530000 | service desk replacement | FIN-116 | 530000 | 0 | Match
PRJ-019 | GIS Mapping Upgrade | 90000 | GIS mapping upgrade | NOT FOUND |  |  | Missing in finance
PRJ-020 | Procurement Portal | 560000 | procurement portal | FIN-117 | 530000 | -30000 | Budget mismatch
PRJ-021 | Document Management Upgrade | 185000 | document management upgrade | FIN-118 | 185000 | 0 | Match
PRJ-022 | Data Governance Framework | 185000 | data governance framework | FIN-119 | 185000 | 0 | Match
PRJ-023 | Electric Vehicle Charging | 130000 | electric vehicle charging | NOT FOUND |  |  | Missing in finance
PRJ-024 | Council Meeting Livestream | 435000 | council meeting livestream | NOT FOUND |  |  | Missing in finance

## Ex3_Risks
Risk ID | Project ID | Owner | Likelihood | Impact | Next Review | Status | Risk Score (L×I) | Rating | Overdue? | Owner Missing? | Project Exists?
R-001 | PRJ-010 | Daniel Park | 5 | 5 | 2026-12-01 | Monitoring | 25 | High | OK | OK | OK
R-002 | PRJ-020 | James Wilson | 1 | 4 | 2026-12-23 | Open | 4 | Low | OK | OK | OK
R-003 | PRJ-015 | Sarah Jones | 3 | 1 | 2026-12-24 | Monitoring | 3 | Low | OK | OK | OK
R-004 | PRJ-014 | James Wilson | 2 | 2 | 2026-07-01 | Open | 4 | Low | OVERDUE | OK | OK
R-005 | PRJ-018 | Mei Chen | 5 | 5 | 2026-09-22 | Open | 25 | High | OVERDUE | OK | OK
R-006 | PRJ-031 |  | 2 | 1 | 2026-06-26 | Open | 2 | Low | OVERDUE | MISSING | ORPHAN
R-007 | PRJ-016 | Sarah Jones | 2 | 2 | 2026-06-09 | Open | 4 | Low | OVERDUE | OK | OK
R-008 | PRJ-009 | Liam O'Brien | 5 | 3 | 2026-08-18 | Monitoring | 15 | High | OVERDUE | OK | OK
R-009 | PRJ-005 | Tom Nguyen | 4 | 5 | 2026-12-17 | Monitoring | 20 | High | OK | OK | OK
R-010 | PRJ-016 |  | 2 | 5 | 2026-10-01 | Monitoring | 10 | Medium | OVERDUE | MISSING | OK
R-011 | PRJ-024 | Priya Sharma | 2 | 2 | 2026-07-16 | Closed | 4 | Low | OK | OK | OK
R-012 | PRJ-023 |  | 1 | 3 | 2026-11-17 | Closed | 3 | Low | OK | MISSING | OK
R-013 | PRJ-017 | James Wilson | 5 | 1 | 2026-07-07 | Open | 5 | Low | OVERDUE | OK | OK
R-014 | PRJ-002 |  | 4 | 5 | 2026-06-25 | Open | 20 | High | OVERDUE | MISSING | OK
R-015 | PRJ-014 |  | 5 | 5 | 2026-07-23 | Open | 25 | High | OVERDUE | MISSING | OK
R-016 | PRJ-014 |  | 4 | 5 | 2026-07-23 | Closed | 20 | High | OK | MISSING | OK
R-017 | PRJ-009 | Liam O'Brien | 4 | 2 | 2026-09-04 | Monitoring | 8 | Medium | OVERDUE | OK | OK
R-018 | PRJ-014 | James Wilson | 2 | 4 | 2026-06-07 | Open | 8 | Medium | OVERDUE | OK | OK
R-019 | PRJ-004 | Tom Nguyen | 2 | 3 | 2026-07-15 | Open | 6 | Low | OVERDUE | OK | OK
R-020 | PRJ-023 | Sarah Jones | 4 | 2 | 2026-11-27 | Open | 8 | Medium | OK | OK | OK
R-021 | PRJ-006 |  | 4 | 3 | 2026-09-07 | Open | 12 | Medium | OVERDUE | MISSING | OK
R-022 | PRJ-010 | Tom Nguyen | 1 | 3 | 2026-10-15 | Monitoring | 3 | Low | OK | OK | OK
R-023 | PRJ-045 | Sarah Jones | 3 | 5 | 2026-10-10 | Closed | 15 | High | OK | OK | ORPHAN
R-024 | PRJ-003 | Liam O'Brien | 1 | 1 | 2026-08-09 | Open | 1 | Low | OVERDUE | OK | OK
R-025 | PRJ-024 | Aisha Khan | 2 | 4 | 2026-12-22 | Open | 8 | Medium | OK | OK | OK
R-026 | PRJ-012 |  | 5 | 5 | 2026-09-23 | Open | 25 | High | OVERDUE | MISSING | OK
R-027 | PRJ-003 | Priya Sharma | 2 | 4 | 2026-06-09 | Open | 8 | Medium | OVERDUE | OK | OK
R-028 | PRJ-020 | Aisha Khan | 1 | 5 | 2026-12-08 | Open | 5 | Low | OK | OK | OK
R-029 | PRJ-009 | Daniel Park | 1 | 3 | 2026-10-14 | Open | 3 | Low | OK | OK | OK
R-030 | PRJ-019 | Priya Sharma | 5 | 2 | 2026-06-06 | Open | 10 | Medium | OVERDUE | OK | OK
R-031 | PRJ-002 | Liam O'Brien | 3 | 3 | 2026-10-25 | Open | 9 | Medium | OK | OK | OK
R-032 | PRJ-009 |  | 2 | 3 | 2026-08-26 | Open | 6 | Low | OVERDUE | MISSING | OK
R-033 | PRJ-009 | Priya Sharma | 1 | 5 | 2026-10-07 | Closed | 5 | Low | OK | OK | OK
R-034 | PRJ-015 | Daniel Park | 1 | 4 | 2026-11-16 | Closed | 4 | Low | OK | OK | OK
R-035 | PRJ-012 | Aisha Khan | 2 | 2 | 2026-08-07 | Open | 4 | Low | OVERDUE | OK | OK
R-036 | PRJ-012 | Priya Sharma | 2 | 1 | 2026-06-21 | Open | 2 | Low | OVERDUE | OK | OK
R-037 | PRJ-013 | Priya Sharma | 1 | 4 | 2026-12-17 | Open | 4 | Low | OK | OK | OK
R-038 | PRJ-019 | Aisha Khan | 1 | 4 | 2026-07-06 | Open | 4 | Low | OVERDUE | OK | OK
R-039 | PRJ-014 | Aisha Khan | 3 | 3 | 2026-10-11 | Open | 9 | Medium | OK | OK | OK
R-040 | PRJ-002 | Liam O'Brien | 3 | 2 | 2026-06-11 | Monitoring | 6 | Low | OVERDUE | OK | OK
Formulas:
Overdue? = IF(AND([Status]<>"Closed",[Next Review]<TODAY()),"OVERDUE","OK")

## Ex4_Summary
Question | Answer | Formula hint
How many projects are in Register_A (incl. duplicate)? | 25 | COUNTA counts non-empty cells
How many projects are Red? | 5 | COUNTIF(range,"Red")
Total budget of the Digital division ($) | 2600000 | SUMIFS(sum_range, criteria_range, criteria)
How many Digital projects are Amber? | 1 | COUNTIFS with 2 conditions (watch the messy 'amber ' → use "Amber*")
Average budget per project ($) | 335200 | AVERAGE
How many risks are still Open? | 26 | COUNTIF
How many open risks are High (score ≥ 15)? | 7 | Needs Ex3_Risks finished first
How many projects are missing from the finance register? | 6 | Needs Ex2_Crosswalk finished first
Total Actual to Date spent across Register_B ($) | 4474000 | SUM

## Answers
ANSWERS: formulas for the first rows of each exercise. Copy them down in your sheet the same way.
Ex1_Clean
Column | Formula (row 3 shown) | What it does
Clean Name =TRIM(PROPER()) | '=TRIM(PROPER(B3)) | PROPER fixes capitals, TRIM removes extra spaces
Clean Status | '=TRIM(PROPER(D3)) | Same cleaning so 'amber ' becomes 'Amber'
Owner Missing? | '=IF(C3="","MISSING","OK") | IF the cell is empty → MISSING
Duplicate ID? | '=IF(COUNTIF($A$2:$A$26,A3)>1,"DUPLICATE","OK") | COUNTIF counts how many times this ID appears; >1 = duplicate
Dates OK? | '=IF(Register_A!F3<Register_A!E3,"END BEFORE START","OK") | End date earlier than start date is impossible
Ex2_Crosswalk
Column | Formula (row 3 shown) | What it does
Match Key (clean name) | '=LOWER(TRIM(B3)) | Lower-case + trimmed so 'CUSTOMER portal ' matches 'Customer Portal'
Finance Code | '=IFERROR(INDEX(Register_B!$A$2:$A$23,MATCH(D3,Register_B!$F$2:$F$23,0)),"NOT FOUND") | MATCH finds the row of the same clean name in Register_B (column F helper), INDEX returns the code from that row. XLOOKUP version: =XLOOKUP(D3, Register_B!$F$2:$F$23, Register_B!$A$2:$A$23, "NOT FOUND")
Budget B ($) | '=IF(E3="NOT FOUND","",INDEX(Register_B!$C$2:$C$23,MATCH(E3,Register_B!$A$2:$A$23,0))) | Looks up the approved budget using the finance code
Difference ($) | '=IF(F3="","",F3-C3) | Finance budget minus PMO budget; not 0 = conflict to log
Result | '=IF(E3="NOT FOUND","Missing in finance",IF(G3<>0,"Budget mismatch","Match")) | Nested IF gives a plain-English status
Ex3_Risks
Column | Formula (row 3 shown) | What it does
Risk Score (L×I) | '=D3*E3 | Standard risk matrix: likelihood × impact
Rating | '=IF(H3>=15,"High",IF(H3>=8,"Medium","Low")) | Nested IF bands: ≥15 High, ≥8 Medium, else Low
Overdue? | '=IF(AND(G3<>"Closed",F3<TODAY()),"OVERDUE","OK") | AND: still open AND review date already passed
Owner Missing? | '=IF(C3="","MISSING","OK") | IF the cell is empty → MISSING
Project Exists? | '=IF(COUNTIF(Register_A!$A$2:$A$26,B3)=0,"ORPHAN","OK") | COUNTIF=0 means this risk points to a project that isn't in the register
Expected findings to check yourself against:
• Register_A: PRJ-009 appears twice (duplicate row).
• Register_A: PRJ-007 has no owner.
• Register_A: PRJ-012 ends before it starts (date error).
• Register_A: PRJ-015 name has extra spaces and lower case; PRJ-004 status is 'amber ' (messy).
• Watch out: PROPER turns 'GIS' into 'Gis' (PRJ-019). Cleaning functions can create new errors, so always eyeball results.
• Crosswalk: 16 projects match exactly; 3 have budget conflicts (PRJ-002, PRJ-016, PRJ-020).
• Crosswalk: 6 show NOT FOUND. Four are truly missing from finance (PRJ-008, 011, 019, 023).
• …but two are the SAME project under a different name: PRJ-013 = FIN-111 'IAM Program', PRJ-024 = FIN-120 'Council Livestreaming'. Formulas can't catch this; you record it manually in the crosswalk and issue log.
• Register_B has 2 projects not in the PMO register at all: FIN-121 Library Self-Checkout Kiosks, FIN-122 Parking Sensor Trial. Log them for management; don't delete them.
• Risk_Log: R-006 (PRJ-031) and R-023 (PRJ-045) point to projects that don't exist (orphans).
• Risk_Log: 9 risks have no owner. Risk ratings: 9 High, 10 Medium, 21 Low.
• Overdue count depends on today's date, so yours will differ over time. That's what TODAY() does.

## Issue_Log
Issue ID | Sheet | Record | Problem | Impact | Suggested Action | Status
ISS-001 | Register_A | PRJ-009 | Duplicate row | Corporate budget overstated by $270,000; totals show 25 projects instead of 24 | PMO to confirm and remove the duplicate | Open
ISS-002 | Register_A | PRJ-007 | No owner assigned | Nobody is accountable for this $160,000 project, so delays, risks and budget issues may go unmanaged | PMO to confirm the owner with the Digital division manager and update the register | Open
ISS-003 | Register_A | PRJ-012 | End date is before start date | Project duration can't be calculated, so schedule and overdue reports for this project are wrong | PMO to confirm correct dates with the project owner and update the register | Open
ISS-004 | Register_A | PRJ-004 | Status entered as "amber " (lowercase, trailing space) | Pivots and charts split Amber into two groups, so the Amber count is understated by 1 | PMO to correct the value; add a Status dropdown to prevent recurrence | Open
ISS-005 | Register_A | PRJ-015 | Name has extra spaces and lowercase | Lookups against other registers can fail, so the project may wrongly show as missing | PMO to correct the name; apply TRIM/PROPER cleaning before matching | Open
ISS-006 | Register_A / Register_B | PRJ-002, PRJ-016, PRJ-020 | Budget differs between PMO and Finance | Finance approved $75,000 less in total (PRJ-002 -$15,000; PRJ-016 -$30,000; PRJ-020 -$30,000); unclear which figure is correct | Finance and PMO to agree the approved budget and document the source for each | Open
ISS-007 | Register_B | PRJ-013 / FIN-111; PRJ-024 / FIN-120 | Same project recorded under different names ("IAM Program", "Council Livestreaming") | Automated matching reports them as missing, overstating gaps between the registers | Linked manually in crosswalk; Finance to adopt PMO project names or record the PMO Project ID | Open
ISS-008 | Register_A | PRJ-008, PRJ-011, PRJ-019, PRJ-023 | Active projects have no Finance record | Spend on 4 projects may be untracked or unapproved | Finance to confirm whether budgets were approved and add records | Open
ISS-009 | Register_B | FIN-121, FIN-122 | Finance projects not in PMO register (Library Self-Checkout Kiosks, Parking Sensor Trial) | $155,000 of approved budget has no PMO oversight | PMO to confirm whether these are projects and add them to the register | Open
ISS-010 | Risk_Log | R-006, R-023 | Risks linked to non-existent projects (PRJ-031, PRJ-045) | These risks can't be reported against any project and may be overlooked | Risk owners to confirm the correct Project ID | Open
ISS-011 | Risk_Log | R-006, R-010, R-012, R-014, R-015, R-016, R-021, R-026, R-032 | 9 risks have no owner | Nobody is responsible for monitoring or mitigating these risks | PMO to assign owners at the next risk review | Open
ISS-012 | Process | All registers | No shared Project ID between PMO and Finance | Every reconciliation depends on name matching, which is slow and error-prone | Add PMO Project ID as a mandatory field in the Finance register | Open
Summary Sheet
1. Reviewed 25 PMO register rows (24 unique projects), 22 Finance records and 40 risks.
2. 16 projects match exactly between PMO and Finance; 2 more were matched manually because they are recorded under different names.
3. 3 projects have budget conflicts totalling $75,000, and 4 active projects have no Finance record.
4. Data quality issues include a duplicate row, a missing owner, an invalid date, inconsistent status values, 9 unowned risks and 2 risks linked to non-existent projects.
5. Decisions needed: agree the correct budgets for 3 projects, confirm funding for 4 unrecorded projects, and require a shared Project ID in both registers.

## finance_Clean
Finance Code | Project Title | PMO Ref | Approved Budget | Forecast | Actual to Date | Last Updated
FIN-103 | Records Digitisation | PRJ-003 | 190000 | 169000 | 105000 | 15/9/2026
FIN-115 | Contract Management Platform | PRJ-017 | 335000 | 399000 | 321000 | 28/9/2026
FIN-114 | Cloud Email Migration | PRJ-016 | 535000 | 626000 | 457000 | 18/9/2026
FIN-113 | Website Accessibility Fixes | PRJ-015 | 465000 | 429000 | 372000 | 28/9/2026
FIN-107 | Mobile Inspections App | PRJ-007 | 160000 | 172000 | 149000 | 25/9/2026
FIN-102 | Payroll System Replacement | PRJ-002 | 360000 | 301000 | 104000 | 15/9/2026
FIN-118 | Document Management Upgrade | PRJ-021 | 185000 | 197000 | 148000 | 15/9/2026
FIN-122 | Parking Sensor Trial |  | 60000 | 52000 | 30000 | 17/9/2026
FIN-111 | Iam Program | PRJ-013 | 395000 | 439000 | 315000 | 28/9/2026
FIN-108 | Grants Management System | PRJ-009 | 270000 | 264000 | 76000 | 19/9/2026
FIN-106 | Data Warehouse Migration | PRJ-006 | 405000 | 468000 | 295000 | 7/9/2026
FIN-110 | Call Centre Modernisation | PRJ-012 | 135000 | 129000 | 39000 | 6/9/2026
FIN-120 | Council Livestreaming | PRJ-024 | 435000 | 482000 | 173000 | 26/9/2026
FIN-104 | Cyber Security Uplift | PRJ-004 | 440000 | 374000 | 114000 | 17/9/2026
FIN-105 | Fleet Telematics Rollout | PRJ-005 | 585000 | 692000 | 436000 | 16/9/2026
FIN-121 | Library Self-Checkout Kiosks |  | 95000 | 98000 | 41000 | 21/9/2026
FIN-109 | Asset Register Cleanup | PRJ-010 | 90000 | 108000 | 57000 | 20/9/2026
FIN-119 | Data Governance Framework | PRJ-022 | 185000 | 209000 | 162000 | 26/9/2026
FIN-101 | Customer Portal Upgrade | PRJ-001 | 455000 | 450000 | 123000 | 6/9/2026
FIN-112 | Budget Reporting Automation | PRJ-014 | 550000 | 627000 | 196000 | 4/9/2026
FIN-116 | Service Desk Replacement | PRJ-018 | 530000 | 547000 | 457000 | 15/9/2026
FIN-117 | Procurement Portal | PRJ-020 | 530000 | 551000 | 304000 | 10/9/2026

## PMO_Clean
Project ID | Initiative Name | Owner Name | Division | Start Date | End Date | Budget | Status | Budget Band
PRJ-001 | Customer Portal Upgrade | Priya Sharma | Digital | 05/06/2025 | 23/04/2026 | 455000 | Green | Large
PRJ-002 | Payroll System Replacement | Liam O'Brien | Digital | 19/06/2025 | 15/11/2025 | 360000 | Green | Medium
PRJ-003 | Records Digitisation | James Wilson | Community | 14/07/2025 | 16/12/2025 | 190000 | Green | Small
PRJ-004 | Cyber Security Uplift | Priya Sharma | Community | 04/10/2025 | 26/05/2026 | 440000 | Amber | Large
PRJ-005 | Fleet Telematics Rollout | Mei Chen | Operations | 02/04/2025 | 12/05/2026 | 585000 | Complete | Large
PRJ-006 | Data Warehouse Migration | Aisha Khan | Corporate | 18/03/2025 | 14/09/2025 | 405000 | Green | Large
PRJ-007 | Mobile Inspections App |  | Digital | 19/10/2025 | 09/01/2027 | 160000 | Green | Small
PRJ-008 | Office Network Refresh | Daniel Park | Community | 02/10/2025 | 12/12/2026 | 170000 | Red | Small
PRJ-009 | Grants Management System | Aisha Khan | Corporate | 19/08/2025 | 06/08/2026 | 270000 | Amber | Medium
PRJ-010 | Asset Register Cleanup | Aisha Khan | Community | 25/12/2025 | 26/08/2026 | 90000 | Red | Small
PRJ-011 | Workforce Planning Tool | James Wilson | Digital | 15/12/2025 | 08/09/2026 | 425000 | Complete | Large
PRJ-012 | Call Centre Modernisation | Daniel Park | Community | 25/03/2025 | 23/02/2025 | 135000 | Green | Small
PRJ-013 | Identity & Access Management | Tom Nguyen | Operations | 03/11/2025 | 29/03/2027 | 395000 | Red | Medium
PRJ-014 | Budget Reporting Automation | Daniel Park | Digital | 16/10/2025 | 06/12/2026 | 550000 | Green | Large
PRJ-015 | Website Accessibility Fixes | James Wilson | Digital | 16/05/2025 | 04/09/2026 | 465000 | Red | Large
PRJ-016 | Cloud Email Migration | Daniel Park | Operations | 19/11/2025 | 02/03/2027 | 565000 | Complete | Large
PRJ-017 | Contract Management Platform | Tom Nguyen | Corporate | 12/11/2025 | 23/03/2026 | 335000 | Green | Medium
PRJ-018 | Service Desk Replacement | Aisha Khan | Corporate | 02/08/2025 | 21/03/2026 | 530000 | Amber | Large
PRJ-019 | GIS Mapping Upgrade | Mei Chen | Community | 13/07/2025 | 22/07/2026 | 90000 | Complete | Small
PRJ-020 | Procurement Portal | Sarah Jones | Operations | 09/09/2025 | 18/03/2026 | 560000 | Complete | Large
PRJ-021 | Document Management Upgrade | Mei Chen | Digital | 22/06/2025 | 02/05/2026 | 185000 | Amber | Small
PRJ-022 | Data Governance Framework | Priya Sharma | Community | 08/03/2025 | 08/06/2026 | 185000 | Amber | Small
PRJ-023 | Electric Vehicle Charging | Sarah Jones | Operations | 10/05/2025 | 09/09/2025 | 130000 | Red | Small
PRJ-024 | Council Meeting Livestream | Priya Sharma | Community | 23/03/2025 | 10/04/2026 | 435000 | Complete | Large

## Spend_Q1
Month | Finance Code | Category | Amount
2026-07-01 | FIN-107 | Licences | 1500
2026-07-01 | FIN-114 | Vendor | 19500
2026-07-01 | FIN-114 | Licences | 7000
2026-07-01 | FIN-119 | Licences | 10000
2026-07-01 | FIN-115 | Labour | 15500
2026-07-01 | FIN-115 | Licences | 9500
2026-07-01 | FIN-120 | Licences | 9000
2026-07-01 | FIN-120 | Labour | 11000
2026-07-01 | FIN-105 | Licences | 10000
2026-07-01 | FIN-102 | Labour | 19000
2026-07-01 | FIN-108 | Vendor | 4000
2026-07-01 | FIN-103 | Vendor | 1500
2026-07-01 | FIN-103 | Labour | 1000
2026-07-01 | FIN-111 | Labour | 2500
2026-07-01 | FIN-101 | Vendor | 14000
2026-07-01 | FIN-101 | Licences | 3000
2026-07-01 | FIN-104 | Licences | 9500
2026-07-01 | FIN-106 | Labour | 11500
2026-07-01 | FIN-106 | Vendor | 1000
2026-07-01 | FIN-113 | Labour | 8500
2026-07-01 | FIN-113 | Licences | 4000
2026-08-01 | FIN-103 | Vendor | 1000
2026-08-01 | FIN-103 | Labour | 9500
2026-08-01 | FIN-115 | Labour | 6500
2026-08-01 | FIN-115 | Licences | 13500
2026-08-01 | FIN-105 | Labour | 5500
2026-08-01 | FIN-121 | Vendor | 9000
2026-08-01 | FIN-102 | Licences | 11500
2026-08-01 | FIN-118 | Vendor | 3000
2026-08-01 | FIN-118 | Labour | 3500
2026-08-01 | FIN-112 | Licences | 8500
2026-08-01 | FIN-111 | Licences | 12500
2026-08-01 | FIN-113 | Licences | 5000
2026-08-01 | FIN-113 | Vendor | 19500
2026-08-01 | FIN-110 | Licences | 13000
2026-08-01 | FIN-110 | Labour | 6500
2026-08-01 | FIN-114 | Vendor | 8000
2026-08-01 | FIN-109 | Licences | 7000
2026-08-01 | FIN-106 | Licences | 18500
2026-08-01 | FIN-116 | Licences | 13000
2026-09-01 | FIN-121 | Vendor | 3000
2026-09-01 | FIN-121 | Labour | 5000
2026-09-01 | FIN-112 | Vendor | 18500
2026-09-01 | FIN-114 | Vendor | 7500
2026-09-01 | FIN-104 | Licences | 1500
2026-09-01 | FIN-115 | Vendor | 14000
2026-09-01 | FIN-113 | Labour | 2000
2026-09-01 | FIN-113 | Licences | 6500
2026-09-01 | FIN-109 | Vendor | 3500
2026-09-01 | FIN-109 | Labour | 12500
2026-09-01 | FIN-103 | Vendor | 11500
2026-09-01 | FIN-111 | Licences | 2000
2026-09-01 | FIN-107 | Vendor | 12000
2026-09-01 | FIN-117 | Labour | 20000
2026-09-01 | FIN-117 | Licences | 3000
2026-09-01 | FIN-118 | Labour | 11000
2026-09-01 | FIN-118 | Vendor | 5000
2026-09-01 | FIN-120 | Labour | 15000
2026-09-01 | FIN-106 | Licences | 5000
2026-09-01 | FIN-106 | Labour | 11500

## Missing_in_Finance
Project ID | Initiative Name | Owner Name | Division | Start Date | End Date | Budget | Status | Budget Band
PRJ-008 | Office Network Refresh | Daniel Park | Community | 02/10/2025 | 12/12/2026 | 170000 | Red | Small
PRJ-011 | Workforce Planning Tool | James Wilson | Digital | 15/12/2025 | 08/09/2026 | 425000 | Complete | Large
PRJ-019 | GIS Mapping Upgrade | Mei Chen | Community | 13/07/2025 | 22/07/2026 | 90000 | Complete | Small
PRJ-023 | Electric Vehicle Charging | Sarah Jones | Operations | 10/05/2025 | 09/09/2025 | 130000 | Red | Small

## Crosswalk
Project ID | Initiative Name | Owner Name | Division | Start Date | End Date | Budget | Status | Budget Band | Finance Code | Approved Budget | Budget Difference
PRJ-001 | Customer Portal Upgrade | Priya Sharma | Digital | 05/06/2025 | 23/04/2026 | 455000 | Green | Large | FIN-101 | 455000 | 0
PRJ-003 | Records Digitisation | James Wilson | Community | 14/07/2025 | 16/12/2025 | 190000 | Green | Small | FIN-103 | 190000 | 0
PRJ-002 | Payroll System Replacement | Liam O'Brien | Digital | 19/06/2025 | 15/11/2025 | 360000 | Green | Medium | FIN-102 | 360000 | 0
PRJ-017 | Contract Management Platform | Tom Nguyen | Corporate | 12/11/2025 | 23/03/2026 | 335000 | Green | Medium | FIN-115 | 335000 | 0
PRJ-016 | Cloud Email Migration | Daniel Park | Operations | 19/11/2025 | 02/03/2027 | 565000 | Complete | Large | FIN-114 | 535000 | -30000
PRJ-004 | Cyber Security Uplift | Priya Sharma | Community | 04/10/2025 | 26/05/2026 | 440000 | Amber | Large | FIN-104 | 440000 | 0
PRJ-015 | Website Accessibility Fixes | James Wilson | Digital | 16/05/2025 | 04/09/2026 | 465000 | Red | Large | FIN-113 | 465000 | 0
PRJ-005 | Fleet Telematics Rollout | Mei Chen | Operations | 02/04/2025 | 12/05/2026 | 585000 | Complete | Large | FIN-105 | 585000 | 0
PRJ-007 | Mobile Inspections App |  | Digital | 19/10/2025 | 09/01/2027 | 160000 | Green | Small | FIN-107 | 160000 | 0
PRJ-006 | Data Warehouse Migration | Aisha Khan | Corporate | 18/03/2025 | 14/09/2025 | 405000 | Green | Large | FIN-106 | 405000 | 0
PRJ-021 | Document Management Upgrade | Mei Chen | Digital | 22/06/2025 | 02/05/2026 | 185000 | Amber | Small | FIN-118 | 185000 | 0
PRJ-008 | Office Network Refresh | Daniel Park | Community | 02/10/2025 | 12/12/2026 | 170000 | Red | Small
PRJ-009 | Grants Management System | Aisha Khan | Corporate | 19/08/2025 | 06/08/2026 | 270000 | Amber | Medium | FIN-108 | 270000 | 0
PRJ-013 | Identity & Access Management | Tom Nguyen | Operations | 03/11/2025 | 29/03/2027 | 395000 | Red | Medium | FIN-111 | 395000 | 0
PRJ-010 | Asset Register Cleanup | Aisha Khan | Community | 25/12/2025 | 26/08/2026 | 90000 | Red | Small | FIN-109 | 90000 | 0
PRJ-011 | Workforce Planning Tool | James Wilson | Digital | 15/12/2025 | 08/09/2026 | 425000 | Complete | Large
PRJ-012 | Call Centre Modernisation | Daniel Park | Community | 25/03/2025 | 23/02/2025 | 135000 | Green | Small | FIN-110 | 135000 | 0
PRJ-014 | Budget Reporting Automation | Daniel Park | Digital | 16/10/2025 | 06/12/2026 | 550000 | Green | Large | FIN-112 | 550000 | 0
PRJ-018 | Service Desk Replacement | Aisha Khan | Corporate | 02/08/2025 | 21/03/2026 | 530000 | Amber | Large | FIN-116 | 530000 | 0
PRJ-022 | Data Governance Framework | Priya Sharma | Community | 08/03/2025 | 08/06/2026 | 185000 | Amber | Small | FIN-119 | 185000 | 0
PRJ-019 | GIS Mapping Upgrade | Mei Chen | Community | 13/07/2025 | 22/07/2026 | 90000 | Complete | Small
PRJ-020 | Procurement Portal | Sarah Jones | Operations | 09/09/2025 | 18/03/2026 | 560000 | Complete | Large | FIN-117 | 530000 | -30000
PRJ-023 | Electric Vehicle Charging | Sarah Jones | Operations | 10/05/2025 | 09/09/2025 | 130000 | Red | Small
PRJ-024 | Council Meeting Livestream | Priya Sharma | Community | 23/03/2025 | 10/04/2026 | 435000 | Complete | Large | FIN-120 | 435000 | 0

## Spend_by_Code
Finance Code | Q1 Spend
FIN-115 | 59000
FIN-106 | 47500
FIN-113 | 45500
FIN-114 | 42000
FIN-120 | 35000
FIN-102 | 30500
FIN-112 | 27000
FIN-103 | 24500
FIN-117 | 23000
FIN-109 | 23000
FIN-118 | 22500
FIN-110 | 19500
FIN-121 | 17000
FIN-101 | 17000
FIN-111 | 17000
FIN-105 | 15500
FIN-107 | 13500
FIN-116 | 13000
FIN-104 | 11000
FIN-119 | 10000
FIN-108 | 4000

## Spend_by_Category
Category | Q1 Spend
Licences | 184000
Labour | 177500
Vendor | 155500

## forecast_by_quarter
Finance Code | Quarter | Forecast
FIN-103 | Q1 FY27 | 51000
FIN-103 | Q2 FY27 | 51000
FIN-103 | Q3 FY27 | 42000
FIN-103 | Q4 FY27 | 25000
FIN-115 | Q1 FY27 | 120000
FIN-115 | Q2 FY27 | 120000
FIN-115 | Q3 FY27 | 100000
FIN-115 | Q4 FY27 | 60000
FIN-114 | Q1 FY27 | 188000
FIN-114 | Q2 FY27 | 188000
FIN-114 | Q3 FY27 | 156000
FIN-114 | Q4 FY27 | 94000
FIN-113 | Q1 FY27 | 129000
FIN-113 | Q2 FY27 | 129000
FIN-113 | Q3 FY27 | 107000
FIN-113 | Q4 FY27 | 64000
FIN-107 | Q1 FY27 | 52000
FIN-107 | Q2 FY27 | 52000
FIN-107 | Q3 FY27 | 43000
FIN-107 | Q4 FY27 | 26000
FIN-102 | Q1 FY27 | 90000
FIN-102 | Q2 FY27 | 90000
FIN-102 | Q3 FY27 | 75000
FIN-102 | Q4 FY27 | 45000
FIN-118 | Q1 FY27 | 59000
FIN-118 | Q2 FY27 | 59000
FIN-118 | Q3 FY27 | 49000
FIN-118 | Q4 FY27 | 30000
FIN-122 | Q1 FY27 | 16000
FIN-122 | Q2 FY27 | 16000
FIN-122 | Q3 FY27 | 13000
FIN-122 | Q4 FY27 | 8000
FIN-111 | Q1 FY27 | 132000
FIN-111 | Q2 FY27 | 132000
FIN-111 | Q3 FY27 | 110000
FIN-111 | Q4 FY27 | 66000
FIN-108 | Q1 FY27 | 79000
FIN-108 | Q2 FY27 | 79000
FIN-108 | Q3 FY27 | 66000
FIN-108 | Q4 FY27 | 40000
FIN-106 | Q1 FY27 | 140000
FIN-106 | Q2 FY27 | 140000
FIN-106 | Q3 FY27 | 117000
FIN-106 | Q4 FY27 | 70000
FIN-110 | Q1 FY27 | 39000
FIN-110 | Q2 FY27 | 39000
FIN-110 | Q3 FY27 | 32000
FIN-110 | Q4 FY27 | 19000
FIN-120 | Q1 FY27 | 145000
FIN-120 | Q2 FY27 | 145000
FIN-120 | Q3 FY27 | 120000
FIN-120 | Q4 FY27 | 72000
FIN-104 | Q1 FY27 | 112000
FIN-104 | Q2 FY27 | 112000
FIN-104 | Q3 FY27 | 94000
FIN-104 | Q4 FY27 | 56000
FIN-105 | Q1 FY27 | 208000
FIN-105 | Q2 FY27 | 208000
FIN-105 | Q3 FY27 | 173000
FIN-105 | Q4 FY27 | 104000
FIN-121 | Q1 FY27 | 29000
FIN-121 | Q2 FY27 | 29000
FIN-121 | Q3 FY27 | 24000
FIN-121 | Q4 FY27 | 15000
FIN-109 | Q1 FY27 | 32000
FIN-109 | Q2 FY27 | 32000
FIN-109 | Q3 FY27 | 27000
FIN-109 | Q4 FY27 | 16000
FIN-119 | Q1 FY27 | 63000
FIN-119 | Q2 FY27 | 63000
FIN-119 | Q3 FY27 | 52000
FIN-119 | Q4 FY27 | 31000
FIN-101 | Q1 FY27 | 135000
FIN-101 | Q2 FY27 | 135000
FIN-101 | Q3 FY27 | 112000
FIN-101 | Q4 FY27 | 68000
FIN-112 | Q1 FY27 | 188000
FIN-112 | Q2 FY27 | 188000
FIN-112 | Q3 FY27 | 157000
FIN-112 | Q4 FY27 | 94000
FIN-116 | Q1 FY27 | 164000
FIN-116 | Q2 FY27 | 164000
FIN-116 | Q3 FY27 | 137000
FIN-116 | Q4 FY27 | 82000
FIN-117 | Q1 FY27 | 165000
FIN-117 | Q2 FY27 | 165000
FIN-117 | Q3 FY27 | 138000
FIN-117 | Q4 FY27 | 83000

## Missing_in_PMO
Finance Code | Project Title | Approved Budget
FIN-122 | Parking Sensor Trial | 60000
FIN-121 | Library Self-Checkout Kiosks | 95000

## Budget_Burn
Project ID | Initiative Name | Owner Name | Division | Start Date | End Date | Budget | Status | Budget Band | Finance Code | Approved Budget | Budget Difference | Q1 Spend | Burn %
PRJ-010 | Asset Register Cleanup | Aisha Khan | Community | 25/12/2025 | 26/08/2026 | 90000 | Red | Small | FIN-109 | 90000 | 0 | 23000 | 0.25556
PRJ-017 | Contract Management Platform | Tom Nguyen | Corporate | 12/11/2025 | 23/03/2026 | 335000 | Green | Medium | FIN-115 | 335000 | 0 | 59000 | 0.17612
PRJ-012 | Call Centre Modernisation | Daniel Park | Community | 25/03/2025 | 23/02/2025 | 135000 | Green | Small | FIN-110 | 135000 | 0 | 19500 | 0.14444
PRJ-003 | Records Digitisation | James Wilson | Community | 14/07/2025 | 16/12/2025 | 190000 | Green | Small | FIN-103 | 190000 | 0 | 24500 | 0.12895
PRJ-021 | Document Management Upgrade | Mei Chen | Digital | 22/06/2025 | 02/05/2026 | 185000 | Amber | Small | FIN-118 | 185000 | 0 | 22500 | 0.12162
PRJ-006 | Data Warehouse Migration | Aisha Khan | Corporate | 18/03/2025 | 14/09/2025 | 405000 | Green | Large | FIN-106 | 405000 | 0 | 47500 | 0.11728
PRJ-015 | Website Accessibility Fixes | James Wilson | Digital | 16/05/2025 | 04/09/2026 | 465000 | Red | Large | FIN-113 | 465000 | 0 | 45500 | 0.097849
PRJ-002 | Payroll System Replacement | Liam O'Brien | Digital | 19/06/2025 | 15/11/2025 | 360000 | Green | Medium | FIN-102 | 360000 | 0 | 30500 | 0.084722
PRJ-007 | Mobile Inspections App |  | Digital | 19/10/2025 | 09/01/2027 | 160000 | Green | Small | FIN-107 | 160000 | 0 | 13500 | 0.084375
PRJ-024 | Council Meeting Livestream | Priya Sharma | Community | 23/03/2025 | 10/04/2026 | 435000 | Complete | Large | FIN-120 | 435000 | 0 | 35000 | 0.08046
PRJ-016 | Cloud Email Migration | Daniel Park | Operations | 19/11/2025 | 02/03/2027 | 565000 | Complete | Large | FIN-114 | 535000 | -30000 | 42000 | 0.078505
PRJ-022 | Data Governance Framework | Priya Sharma | Community | 08/03/2025 | 08/06/2026 | 185000 | Amber | Small | FIN-119 | 185000 | 0 | 10000 | 0.054054
PRJ-014 | Budget Reporting Automation | Daniel Park | Digital | 16/10/2025 | 06/12/2026 | 550000 | Green | Large | FIN-112 | 550000 | 0 | 27000 | 0.049091
PRJ-020 | Procurement Portal | Sarah Jones | Operations | 09/09/2025 | 18/03/2026 | 560000 | Complete | Large | FIN-117 | 530000 | -30000 | 23000 | 0.043396
PRJ-013 | Identity & Access Management | Tom Nguyen | Operations | 03/11/2025 | 29/03/2027 | 395000 | Red | Medium | FIN-111 | 395000 | 0 | 17000 | 0.043038
PRJ-001 | Customer Portal Upgrade | Priya Sharma | Digital | 05/06/2025 | 23/04/2026 | 455000 | Green | Large | FIN-101 | 455000 | 0 | 17000 | 0.037363
PRJ-005 | Fleet Telematics Rollout | Mei Chen | Operations | 02/04/2025 | 12/05/2026 | 585000 | Complete | Large | FIN-105 | 585000 | 0 | 15500 | 0.026496
PRJ-004 | Cyber Security Uplift | Priya Sharma | Community | 04/10/2025 | 26/05/2026 | 440000 | Amber | Large | FIN-104 | 440000 | 0 | 11000 | 0.025
PRJ-018 | Service Desk Replacement | Aisha Khan | Corporate | 02/08/2025 | 21/03/2026 | 530000 | Amber | Large | FIN-116 | 530000 | 0 | 13000 | 0.024528
PRJ-009 | Grants Management System | Aisha Khan | Corporate | 19/08/2025 | 06/08/2026 | 270000 | Amber | Medium | FIN-108 | 270000 | 0 | 4000 | 0.014815
PRJ-023 | Electric Vehicle Charging | Sarah Jones | Operations | 10/05/2025 | 09/09/2025 | 130000 | Red | Small
PRJ-008 | Office Network Refresh | Daniel Park | Community | 02/10/2025 | 12/12/2026 | 170000 | Red | Small
PRJ-011 | Workforce Planning Tool | James Wilson | Digital | 15/12/2025 | 08/09/2026 | 425000 | Complete | Large
PRJ-019 | GIS Mapping Upgrade | Mei Chen | Community | 13/07/2025 | 22/07/2026 | 90000 | Complete | Small

## Dashboard
Projects missing from Finance | 4
Finance projects missing from PMO | 2
Total Q1 spend | 517000
Budget by Division and Size
Sum of Budget | Column Labels
Row Labels | Small | Medium | Large | Grand Total
Community | 860000 |  | 875000 | 1735000
Corporate |  | 605000 | 935000 | 1540000
Digital | 345000 | 360000 | 1895000 | 2600000
Operations | 130000 | 395000 | 1710000 | 2235000
Grand Total | 1335000 | 1360000 | 5415000 | 8110000
Key Findings
# | Finding | Severity | Action
1 | 20 of 24 PMO projects match Finance on Project ID | Low | None, reconciliation working
2 | 2 budget conflicts of $30,000 each (PRJ-016, PRJ-020) | Medium | Finance & PMO to agree approved budgets
3 | 4 projects have no Finance record; PRJ-011 and PRJ-019 already Complete | High | Finance to confirm spend was approved
4 | 2 Finance projects ($155,000) have no PMO oversight | Medium | PMO to review and register FIN-121, FIN-122
5 | PRJ-010 has spent 26% of budget in one quarter | Medium | Monitor monthly for overspend